## Executive Summary
BANKING MICROSERVICES POC — TIMESHEET & DATE DELIVERY PLAN
Java Spring Boot ¦ PostgreSQL ¦ Dapr Service Invocation ¦ Docker Compose (6 Containers) ¦ Concurrency Control
1. PROJECT GOAL & SCOPE (SIMPLE 2-MICROSERVICE POC)
Project Objective | Build a lightweight 2-microservice banking system to demonstrate how Dapr connects microservices and how database locking stops money from dropping below zero during simultaneous withdrawals.
Microservice 1: Transaction Service | Spring Boot app (port 8081). Receives withdrawal requests from Postman or browser, validates inputs, and sends the request to Accounting Service via Dapr.
Microservice 2: Accounting Service | Spring Boot app (port 8082). Only service with PostgreSQL access. Checks account balance, locks the account row during deduction, and logs transaction history.
Step 1: Direct HTTP Baseline | First, services communicated directly (http://accounting-app:8082). This proved that the withdrawal math and JSON responses worked before adding extra tools.
Step 2: Dapr Service Invocation | Next, services were upgraded to Dapr (http://localhost:3500/v1.0/invoke/accounting-service/method/...). Neither service hardcodes the other's IP or port.
Docker Parting Out (6 Containers) | The system runs smoothly in Docker Compose parted into 6 containers: 1 PostgreSQL, 1 Dapr placement directory, 2 Spring Boot apps, and 2 Dapr sidecars.
Concurrency & Safety Goal | Ensure that if 2 withdrawal requests arrive at the exact same second for the same account, the balance NEVER drops below zero and no money is lost.
2. KEY DATES & DELIVERY MILESTONES (COMPLETION UNDER SEP 25, 2026)
Project Period | Sep 15, 2026 – Sep 25, 2026 |  | Tracking Format | Date-based milestones (No hourly clocking)
Working Days | 9 Working Days (Tue Sep 15 to Fri Sep 25) |  | Target Handover | On or before Sep 25, 2026
Week 1 Milestone | Sep 18, 2026 (Friday) — Direct HTTP & Dapr invocation working cleanly |  | Week 2 Milestone | Sep 21, 2026 (Monday) — Concurrency protection & audit history tested
Final Demo & Handover | Sep 25, 2026 (Friday) — Senior walkthrough (Rajeev Ranjan) & sign-off |  | Current Status | ON TRACK (Ready for Sep 25, 2026)
3. DELIVERY ROADMAP PHASES (9-DAY DATE TIMELINE)
Phase | Date | Simple Goal |  | Key Deliverables | Status
Phase 1: Project Creation | Sep 15 (Tue) | Create Spring Boot projects for Transaction & Accounting services |  | Both services created, configured, and compile cleanly | DONE
Phase 2: Docker Setup | Sep 16 (Wed) | Part out 6 Docker containers (database, apps, sidecars, placement) |  | docker-compose.yml running, 6 containers green, seed accounts ready | IN PROGRESS
Phase 3: Communication Progression | Sep 17 (Thu) | First connect via direct HTTP, verify it works, then upgrade to Dapr |  | Direct HTTP tested, Dapr invocation working, duplicate check enabled | TO DO
Phase 4: Concurrency Lock & Testing | Sep 18 (Fri) | Add SELECT FOR UPDATE row locking and test overdraft protection |  | Database locking in repository, Week 1 progress check complete | MILESTONE
Phase 5: Concurrency Verification | Sep 21 (Mon) | Test simultaneous withdrawals to verify balance never goes below zero |  | Concurrency test script verified, DB audit logs accurate | TO DO
Phase 6: Code Cleanup & Logs | Sep 22 (Tue) | Clean up code and add simple, friendly console logs |  | Clean codebase, clear logs showing Dapr hops & balance deductions | TO DO
Phase 7: Simple Documentation | Sep 23 (Wed) | Write easy README with clear startup steps and architecture diagram |  | README.md ready with clear commands for anyone to test | TO DO
Phase 8: Cold Restart & Demo Practice | Sep 24 (Thu) | Test clean cold startup in Docker and rehearse walkthrough talking points |  | 5/5 test cases passing, 1-page demo talking points sheet | TO DO
Phase 9: Live Demo & Handover | Sep 25 (Fri) | Live demo presentation to senior (Rajeev Ranjan) and project sign-off |  | Live demo completed, final project handover under date Sep 25 | DEADLINE

## Day-by-Day Timesheet
DAILY TIMESHEET & DATE-BASED WORK PLAN (SEP 15 – SEP 25, 2026)
Date | Day | Phase | Task ID | Task Description (Simple Language) | Expected Deliverable | Status
15-Sep-2026 | Tuesday | Learn | T01 | Learn POC goals & how Dapr connects microservices without hardcoded URLs | Architecture notes & clear mental model | DONE
15-Sep-2026 | Tuesday | Setup | T02 | Check prerequisites on local PC: Java 17, Docker Desktop, Maven, and IDE | Development environment ready | DONE
15-Sep-2026 | Tuesday | Code | T03 | Create Transaction Service: handles client withdrawal requests (port 8081) | transaction-service project created | DONE
15-Sep-2026 | Tuesday | Code | T04 | Create Accounting Service: checks balances & deducts money from DB (port 8082) | accounting-service project created | DONE
15-Sep-2026 | Tuesday | Code | T05 | Configure application properties: port 8081 for Transaction, port 8082 for Accounting | application.yml files written for both services | DONE
15-Sep-2026 | Tuesday | Code | T06 | Verify Maven compilation locally to ensure zero syntax or dependency errors | Both microservices build cleanly with Maven | DONE
16-Sep-2026 | Wednesday | Setup | T07 | Write simple Dockerfiles to containerize both Java services | Dockerfiles added to both service folders | IN PROGRESS
16-Sep-2026 | Wednesday | Setup | T08 | Set up Docker Compose with PostgreSQL database (5432) and Dapr discovery (50005) | banking-postgres and dapr-placement configured | IN PROGRESS
16-Sep-2026 | Wednesday | Setup | T09 | Add starter bank accounts in PostgreSQL: ACC001 (₹5,000) and ACC002 (₹10,000) | Starter accounts created via database/init.sql | IN PROGRESS
16-Sep-2026 | Wednesday | Setup | T10 | Attach Dapr sidecars to each service in Docker Compose using shared network mode | Sidecars (transaction-dapr, accounting-dapr) mapped | TO DO
16-Sep-2026 | Wednesday | Setup | T11 | Start all 6 containers with docker compose up and verify they run healthy | All 6 containers running green in Docker Desktop | TO DO
17-Sep-2026 | Thursday | Code | T12 | Step 1 (Direct HTTP): Connect services directly via HTTP to confirm basic math works | Verified direct REST communication works | TO DO
17-Sep-2026 | Thursday | Code | T13 | Write withdrawal logic in Accounting Service: check account exists & balance is enough | Core withdrawal balance deduction implemented | TO DO
17-Sep-2026 | Thursday | Code | T14 | Step 2 (Dapr Upgrade): Switch from direct HTTP to Dapr Service Invocation | Services fully decoupled via Dapr sidecars | TO DO
17-Sep-2026 | Thursday | Code | T15 | Add duplicate request check (Idempotency): check requestId to prevent double-charging | Duplicate withdrawal protection enabled | TO DO
17-Sep-2026 | Thursday | Test | T16 | Manual test: withdraw ₹500 from ACC001 via cURL, confirm balance becomes ₹4,500 | First successful withdrawal verified end-to-end | TO DO
18-Sep-2026 | Friday | Learn | T17 | Learn why simultaneous withdrawals cause negative balance (race conditions) | Clear understanding of concurrent banking issues | TO DO
18-Sep-2026 | Friday | Code | T18 | Add database row lock (SELECT FOR UPDATE) so simultaneous requests wait their turn | Row-level locking implemented in database layer | TO DO
18-Sep-2026 | Friday | Test | T19 | Test overdraft: try withdrawing ₹10,000 when balance is ₹4,500 (verify clean error) | Verified balance remains untouched on overdraft | TO DO
18-Sep-2026 | Friday | Test | T20 | Test wrong account: try withdrawing from non-existent ACC999 (verify 404 response) | Error handling for non-existent accounts verified | TO DO
18-Sep-2026 | Friday | Review | T21 | Week 1 check: confirm all code compiles, restart Docker cleanly, draft notes for mentor | Week 1 baseline achieved & verified | MILESTONE
21-Sep-2026 | Monday | Test | T22 | Write a simple script (test-poc.ps1) to send 2 withdrawal requests at the exact same second | Automated test script for concurrency | TO DO
21-Sep-2026 | Monday | Test | T23 | Run concurrency test: two ₹3,000 requests on ₹5,000 balance (1 passes, 1 fails, balance ₹2,000) | Confirmed: balance never drops below zero | TO DO
21-Sep-2026 | Monday | Test | T24 | Test duplicate requests sent at once: verify identical requestId is safely blocked | Verified unique requestId prevents double deduction | TO DO
21-Sep-2026 | Monday | Test | T25 | Inspect PostgreSQL database: check withdrawal_transactions table for complete audit log | Database transaction history verified accurate | TO DO
22-Sep-2026 | Tuesday | Code | T26 | Clean up code: remove unused imports, format files, make code easy to read | Clean, readable code in both services | TO DO
22-Sep-2026 | Tuesday | Code | T27 | Add friendly console logs showing step-by-step progress during each request | Console logs are easy to follow during demo | TO DO
22-Sep-2026 | Tuesday | Test | T28 | Re-run all tests to confirm clean code did not break any functionality | All tests passing on cleaned code | TO DO
22-Sep-2026 | Tuesday | Setup | T29 | Check Swagger UI on both services (ports 8081 & 8082) for interactive visual testing | Interactive Swagger UI available in browser | TO DO
23-Sep-2026 | Wednesday | Docs | T30 | Write simple README.md: project overview, prerequisites, and how to run with Docker | Easy-to-follow README.md documentation | TO DO
23-Sep-2026 | Wednesday | Docs | T31 | Draw visual diagram showing: User -> Transaction -> Dapr -> Accounting -> PostgreSQL | Visual architecture flow included in README | TO DO
23-Sep-2026 | Wednesday | Test | T32 | Follow README instructions from scratch to ensure anyone can run the project easily | Verified documentation works without missing steps | TO DO
23-Sep-2026 | Wednesday | Docs | T33 | Clean up repository: check .gitignore, remove temporary test files | Clean repository ready for review | TO DO
24-Sep-2026 | Thursday | Test | T34 | Cold restart test: test 'docker compose down -v' then 'docker compose up' from zero | Verified fresh bootstrap works smoothly | TO DO
24-Sep-2026 | Thursday | Test | T35 | Run complete 5-test checklist: normal withdrawal, duplicate, overdraft, missing account, concurrency | 5 out of 5 test scenarios verified 100% passing | TO DO
24-Sep-2026 | Thursday | Demo | T36 | Prepare 1-page talking points: simple explanations for 'Why Dapr?' and 'Why database locking?' | 1-page quick-reference sheet for senior demo | TO DO
24-Sep-2026 | Thursday | Demo | T37 | Practice demo walkthrough: rehearse explaining architecture, showing Docker, and running cURL | Confident, clear walkthrough rehearsed | TO DO
25-Sep-2026 | Friday | Demo | T38 | Morning system check: start Docker stack, confirm all 6 containers healthy, run 1 quick test | System 100% ready for presentation | TO DO
25-Sep-2026 | Friday | Demo | T39 | LIVE POC DEMO TO SENIOR (Rajeev Ranjan): explain 2 microservices, Dapr, and concurrency safety | Live demonstration successfully presented | MILESTONE
25-Sep-2026 | Friday | Review | T40 | Gather senior feedback and note down any suggestions or questions | Demo feedback captured | TO DO
25-Sep-2026 | Friday | Code | T41 | Make any minor tweaks requested by senior during the demo | Senior feedback items completed | TO DO
25-Sep-2026 | Friday | Deliver | T42 | Final project handover: share GitHub link, README, and timesheet with senior for sign-off | Official Project Handover Complete (Under Sep 25) | DEADLINE
TOTAL PROJECT TIMELINE: |  |  |  | 9 Working Days (Sep 15 – Sep 25, 2026) · Target Completion Date: Sep 25, 2026

## Master Task WBS
MASTER WORK BREAKDOWN STRUCTURE (WBS) — 15 POC TASKS
Task ID | Task Name (Simple Language) | Phase | Target Date | Priority | Why It Matters (Simple Terms) | Status
T01 | Learn POC goals and understand Dapr sidecar basics | Learn | Day 1 (Sep 15) | High | Explains how microservices talk through sidecars without hardcoded IPs | DONE
T02 | Check prerequisites: Java 17, Docker Desktop, IDE | Setup | Day 1 (Sep 15) | High | Ensures computer is ready to run all 6 containers | DONE
T03 | Create Transaction Service Spring Boot project | Code | Day 1 (Sep 15) | Critical | Public endpoint that accepts withdrawal requests (/api/v1/transactions/withdraw) | DONE
T04 | Create Accounting Service Spring Boot project with JPA | Code | Day 1 (Sep 15) | Critical | Banking engine that checks balances & updates database | DONE
T05 | Write Dockerfiles & configure PostgreSQL database | Setup | Day 2 (Sep 16) | Critical | Initializes database schema and starter accounts (ACC001) | IN PROGRESS
T06 | Set up 6 containers in Docker Compose (apps + sidecars + placement) | Setup | Day 2 (Sep 16) | Critical | Connects sidecars and apps using shared network mode | TO DO
T07 | Step 1: Test Direct HTTP communication between microservices | Code | Day 3 (Sep 17) | High | Proves basic withdrawal calculation works before adding Dapr | TO DO
T08 | Step 2: Upgrade to Dapr Service Invocation & duplicate request check | Code | Day 3 (Sep 17) | Critical | Decouples services completely and prevents double deductions | TO DO
T09 | Add database row locking (SELECT ... FOR UPDATE) in repository | Code | Day 4 (Sep 18) | Critical | Locks account row so simultaneous requests wait in queue | TO DO
T10 | Manual testing: normal withdrawal, overdraft & non-existent account | Test | Day 4 (Sep 18) | High | Confirms proper responses (HTTP 200, 400, 404) | TO DO
T11 | Concurrency test: send 2 simultaneous withdrawals to verify balance | Test | Day 5 (Sep 21) | Critical | Proves balance never goes below zero during race conditions | TO DO
T12 | Clean up code, format files & add friendly console logs | Code | Day 6 (Sep 22) | Medium | Ensures console logs clearly show every transaction step | TO DO
T13 | Write simple README.md with startup steps & architecture diagram | Docs | Day 7 (Sep 23) | High | Provides clear instructions so anyone can run the POC easily | TO DO
T14 | End-to-end dry run: test cold start & prepare demo talking points | Demo | Day 8 (Sep 24) | High | Validates clean bootstrap and prepares answers for senior | TO DO
T15 | Live demo walkthrough with senior (Rajeev Ranjan) & project sign-off | Demo | Day 9 (Sep 25) | Critical | Demonstrates working POC and achieves official sign-off | DEADLINE
TOTAL CORE POC TASKS: |  |  | 15 Core Tasks · Target Handover Under Sep 25, 2026

## Concurrency & Test Plan
CONCURRENCY, DOCKER & COMMUNICATION SPECIFICATION
Explaining Docker Containers, Direct HTTP vs Dapr Progression, and Database Row Locking
1. DOCKER ARCHITECTURE — THE 6 CONTAINERS PARTED OUT
# | Container Name | Technology | Port(s) | Network Mode | Purpose & Working Mechanism
1 | banking-postgres | PostgreSQL 15 Alpine | 5432:5432 | banking-net | Database for accounts & transactions. Runs database/init.sql on startup to seed ACC001 (₹5,000).
2 | dapr-placement | daprio/dapr:1.13.0 | 50005:50005 | banking-net | Dapr placement & discovery service. Acts as the directory so sidecars discover each other without hardcoded IPs.
3 | transaction-app | Spring Boot (Java 17) | 8081:8081 | banking-net | Microservice 1: Receives client withdrawal requests, validates inputs, and calls Accounting via Dapr.
4 | transaction-dapr | daprio/daprd:1.13.0 | 3500 (HTTP) | service:transaction-app | Sidecar for Microservice 1: Shares network with transaction-app. Reached via localhost:3500.
5 | accounting-app | Spring Boot (Java 17) | 8082:8082 | banking-net | Microservice 2: Owns PostgreSQL database. Executes SELECT FOR UPDATE locking and balance deduction.
6 | accounting-dapr | daprio/daprd:1.13.0 | 3501 (HTTP) | service:accounting-app | Sidecar for Microservice 2: Shares network with accounting-app. Forwards received calls to localhost:8082.
2. COMMUNICATION EVOLUTION: STEP 1 (DIRECT HTTP) vs. STEP 2 (DAPR UPGRADE)
Step 1: Direct HTTP (Starting Baseline) | Transaction Service called 'http://accounting-app:8082/api/v1/accounting/withdraw' directly via RestTemplate. We did this FIRST to test the business logic, JSON models, and database balance deduction without any extra runtime dependencies.
Drawback of Direct HTTP | Tight coupling: Transaction Service had to hardcode the exact hostname and port (accounting-app:8082). If the service moves, port changes, or network changes, code must be updated and recompiled.
Step 2: Dapr Service Invocation (Upgrade) | Once direct HTTP worked, we switched to Dapr. Transaction Service calls 'http://localhost:3500/v1.0/invoke/accounting-service/method/...'. The local Dapr sidecar queries placement and forwards the call across the network to accounting-dapr, which delivers it locally to port 8082.
Key Benefit of Dapr | Zero hardcoded URLs or ports! The caller only knows the logical app-id ('accounting-service'). Dapr automatically provides service discovery, automatic retries, and distributed tracing across containers.
3. CONCURRENCY LOAD & SAFETY TEST SCENARIOS (EASY TO RUN & VERIFY)
Scenario ID | Test Scenario | Initial Balance | Withdrawal Request | Expected Outcome | Final Balance | Validation Rule
TC-01 | Single User Normal Withdrawal | ₹5,000.00 | 1 request for ₹500.00 | HTTP 200 OK (SUCCESS) | ₹4,500.00 | Balance reduced by exactly ₹500, transaction logged
TC-02 | Duplicate Request Check (Idempotency) | ₹4,500.00 | Send exact same requestId twice | 1st: HTTP 200, 2nd: Cached HTTP 200 | ₹4,500.00 | Second request returns saved result; NO double deduction
TC-03 | Insufficient Balance (Overdraft) | ₹4,500.00 | 1 request for ₹10,000.00 | HTTP 200 FAILED (INSUFFICIENT_BALANCE) | ₹4,500.00 | Balance untouched, friendly error 'Insufficient balance'
TC-04 | Non-Existent Account ID | N/A | 1 request for ACC999 | HTTP 200 FAILED (ACCOUNT_NOT_FOUND) | N/A | Clean error response, no database locks left open
TC-05 | Concurrent Withdrawal Safety Test | ₹5,000.00 | 2 simultaneous requests for ₹3,000 | 1x SUCCESS, 1x FAILED | ₹2,000.00 | Balance NEVER drops below zero; exactly one succeeds