## Executive Summary
BANKING MICROSERVICES POC — TIMESHEET & DELIVERY PLAN
Java Spring Boot ¦ PostgreSQL ¦ Dapr Service Invocation ¦ Docker Compose ¦ Pessimistic Concurrency
1. PROJECT CONTEXT & EMAIL DIRECTIVE (Rajeev Ranjan)
Stakeholder Directive | Create a 2-microservice banking transaction architecture with Dapr and concurrency handling.
Service 1: Withdrawal Service | Accepts withdrawal HTTP payload, validates request, routes invocation to Accounting Service via Dapr.
Service 2: Accounting Service | Direct DB connection to PostgreSQL, executes balance deduction with Pessimistic Locking (SELECT FOR UPDATE).
Communication Protocol | Dapr Service Invocation (/v1.0/invoke/accounting-service/method/...) - zero direct service-to-service coupling.
Core Architectural Focus | Concurrency resilience: Ensure multiple simultaneous user requests prevent double-spending & race conditions.
Execution Environment | Local Personal PC with Docker Desktop, Java 17+, PostgreSQL container, and Dapr sidecars.
2. SCHEDULE METRICS & KEY MILESTONES
Working Period | Sep 15, 2026 – Sep 30, 2026 |  | Working Hours/Day | 9:30 AM – 18:00 (8.5 hrs/day, 1h lunch)
Working Days Available | 12 Days (Monday – Friday) |  | Total Productive Hours | ~90 Productive Hours (7.5h net/day)
Estimated Core Dev Time | 12 – 15 Hours (3 Days) |  | Buffer / Polish Margin | 9 Working Days (~67.5 Hours)
Initial Target Delivery | September 18, 2026 (End of Week 1) |  | Stakeholder Demo Target | September 21, 2026 (Monday)
Hard Final Deadline | September 30, 2026 (Tuesday) |  | Delivery Confidence | HIGH (5.5x Buffer Margin)
3. DELIVERY ROADMAP PHASES
Phase | Dates | Target Goal |  | Key Deliverables | Status
Phase 1: Build & Scaffold | Sep 15 (Tue) | Generate both Spring Boot services & Docker files |  | Withdrawal Service, Accounting Service, POMs, JPA Repos | IN PROGRESS
Phase 2: Multi-Container & Dapr | Sep 16 (Wed) | Docker Compose up, 5 containers running, DB seeded |  | docker-compose.yml, Dapr sidecar configs, Swagger UI | PLANNED
Phase 3: Concurrency & Testing | Sep 17 (Thu) | Validate Pessimistic Locking & Postman test runs |  | 10-thread concurrency load test, zero race condition proof | PLANNED
Phase 4: Hardening & Docs | Sep 18 (Fri) | Demo preparation, README & Architecture Diagrams |  | Talking points for Rajeev, visual architecture diagram, runbook | PLANNED
Phase 5: Stakeholder Demo | Sep 21 (Mon) | Live demonstration to Rajeev Ranjan & Nirakar Dash |  | Successful live withdrawal, concurrency demo, Q&A defense | PLANNED
Phase 6: Buffer & Iterations | Sep 22 - Sep 29 | Address feedback, resilience tuning, metric additions |  | Refinements, retry policies, metrics logging | BUFFER
Phase 7: Final Handover | Sep 30 (Tue) | Official POC sign-off & repository submission |  | Final release tag, Postman collection, clean repo | DEADLINE

## Day-by-Day Timesheet
DAILY TIMESHEET & WORK SCHEDULE (9:30 AM – 18:00 PM)
Date | Day | Time Slot | Phase | Task ID | Task / Activity Description | Hours | Expected Deliverable | Status
15-Sep-2026 | Tuesday | 09:30 – 10:00 | Learn | T01 | Read Dapr concepts: Service Invocation, sidecars, app-id, mTLS | 0.5 | Architecture notes & diagram mental model | IN PROGRESS
15-Sep-2026 | Tuesday | 10:00 – 10:30 | Setup | T02 | Prerequisites verification: Java 17+, Docker Desktop running, Dapr CLI | 0.5 | Local environment verified | IN PROGRESS
15-Sep-2026 | Tuesday | 10:30 – 11:30 | Code | T03 | Generate Withdrawal Service: Spring Boot REST API, WithdrawalRequest/Response | 1 | WithdrawalService + Web Controller written | IN PROGRESS
15-Sep-2026 | Tuesday | 11:30 – 13:00 | Code | T04 | Generate Accounting Service: Account & Transaction JPA Entities + PostgreSQL config | 1.5 | Accounting models, AccountRepository written | IN PROGRESS
15-Sep-2026 | Tuesday | 13:00 – 14:00 | Break | - | Lunch & Personal Break | 1 | - | BREAK
15-Sep-2026 | Tuesday | 14:00 – 15:30 | Code | T05 | Implement Concurrency Lock: @Lock(PESSIMISTIC_WRITE) on AccountRepository | 1.5 | Pessimistic row locking logic implemented | TO DO
15-Sep-2026 | Tuesday | 15:30 – 16:30 | Code | T06 | Dapr Invocation Client: RestTemplate routing to localhost:3500 Dapr sidecar | 1 | Dapr HTTP invocation client wired | TO DO
15-Sep-2026 | Tuesday | 16:30 – 18:00 | Code | T07 | Add Swagger / OpenAPI UI (SpringDoc 2.5.0) to both microservices | 1.5 | Interactive /swagger-ui.html for both apps | TO DO
16-Sep-2026 | Wednesday | 09:30 – 11:00 | Setup | T08 | Write Docker Compose + Dapr Sidecar YAML configs (5 containers total) | 1.5 | docker-compose.yml + dapr component YAMLs | TO DO
16-Sep-2026 | Wednesday | 11:00 – 12:30 | Setup | T09 | Run docker-compose up --build, resolve port mappings, networks & startup order | 1.5 | 5 healthy containers in Docker Desktop | TO DO
16-Sep-2026 | Wednesday | 12:30 – 13:00 | Test | T10 | Verify PostgreSQL schema generation & seed sample accounts (ACC-001, ACC-002) | 0.5 | DB accounts initialized with seed balance | TO DO
16-Sep-2026 | Wednesday | 13:00 – 14:00 | Break | - | Lunch & Personal Break | 1 | - | BREAK
16-Sep-2026 | Wednesday | 14:00 – 15:30 | Test | T11 | Happy Path Testing via Postman: POST /api/withdraw ($500 withdrawal) | 1.5 | HTTP 200, balance reduced, transaction logged | TO DO
16-Sep-2026 | Wednesday | 15:30 – 17:00 | Test | T12 | Negative Path Testing: Insufficient funds ($10,000 withdrawal) & invalid account | 1.5 | HTTP 400 & HTTP 404 proper error payloads | TO DO
16-Sep-2026 | Wednesday | 17:00 – 18:00 | Docs | T13 | Document initial findings & Postman collection export | 1 | Exported Postman test suite JSON | TO DO
17-Sep-2026 | Thursday | 09:30 – 11:30 | Test | T14 | Concurrency Testing: Multi-threaded load test (10 simultaneous requests) | 2 | Verified zero double-spending & exact DB balance | TO DO
17-Sep-2026 | Thursday | 11:30 – 13:00 | Code | T15 | Read & audit locking behavior, verify transaction isolation levels | 1.5 | Deep-dive code review & lock verification | TO DO
17-Sep-2026 | Thursday | 13:00 – 14:00 | Break | - | Lunch & Personal Break | 1 | - | BREAK
17-Sep-2026 | Thursday | 14:00 – 16:00 | Docs | T16 | Write comprehensive README.md: Architecture diagram, run steps, API contracts | 2 | Production-grade README with Mermaid diagrams | TO DO
17-Sep-2026 | Thursday | 16:00 – 18:00 | Demo | T17 | Prepare talking points for Rajeev: 'Why Dapr? Why Pessimistic Locking?' | 2 | Executive talking points document ready | TO DO
18-Sep-2026 | Friday | 09:30 – 11:30 | Demo | T18 | End-to-end dry-run demo: Clean startup, live execution, log verification | 2 | Dry-run demo video / recording checklist | TO DO
18-Sep-2026 | Friday | 11:30 – 13:00 | Polish | T19 | Log formatting: Add correlation IDs and readable Dapr sidecar trace logs | 1.5 | Clean, readable console logs for presentation | TO DO
18-Sep-2026 | Friday | 13:00 – 14:00 | Break | - | Lunch & Personal Break | 1 | - | BREAK
18-Sep-2026 | Friday | 14:00 – 16:30 | Review | T20 | Week 1 Internal Milestone Review & POC Baseline Freeze | 2.5 | Tag repository: v1.0-poc-baseline | TO DO
18-Sep-2026 | Friday | 16:30 – 18:00 | Buffer | T21 | Week 1 wrap-up, weekly status report email draft to Rajeev | 1.5 | Status report ready for Monday review | BUFFER
21-Sep-2026 | Monday | 09:30 – 11:00 | Demo | T22 | Pre-demo system validation & warm-up run | 1.5 | Zero-error state confirmed | TO DO
21-Sep-2026 | Monday | 11:00 – 12:30 | Demo | T23 | STAKEHOLDER LIVE DEMO: Walkthrough for Rajeev Ranjan & Nirakar Dash | 1.5 | Live demonstration successfully presented | MILESTONE
21-Sep-2026 | Monday | 12:30 – 13:00 | Review | T24 | Collect demo feedback, capture questions & action items | 0.5 | Feedback register documented | TO DO
21-Sep-2026 | Monday | 13:00 – 14:00 | Break | - | Lunch & Personal Break | 1 | - | BREAK
21-Sep-2026 | Monday | 14:00 – 18:00 | Code | T25 | Feedback Implementation Session 1: Address immediate stakeholder comments | 4 | Initial feedback adjustments implemented | TO DO
22-Sep-2026 | Tuesday | 09:30 – 13:00 | Code | T26 | Enhance Observability: Add Spring Actuator metrics & health probes to Dapr | 3.5 | Custom metrics and actuator health checks | TO DO
22-Sep-2026 | Tuesday | 13:00 – 14:00 | Break | - | Lunch & Personal Break | 1 | - | BREAK
22-Sep-2026 | Tuesday | 14:00 – 18:00 | Test | T27 | High-load concurrency test: 50 concurrent requests with connection pool tuning | 4 | High-load test report & HikariCP pool audit | TO DO
23-Sep-2026 | Wednesday | 09:30 – 13:00 | Setup | T28 | Dapr Resiliency Policies: Configure timeout & retry policies in component YAML | 3.5 | Resiliency spec applied to sidecars | BUFFER
23-Sep-2026 | Wednesday | 13:00 – 14:00 | Break | - | Lunch & Personal Break | 1 | - | BREAK
23-Sep-2026 | Wednesday | 14:00 – 18:00 | Polish | T29 | Exception Handling Polish: RFC 7807 ProblemDetails compliance | 4 | Standardized JSON error responses | BUFFER
24-Sep-2026 | Thursday | 09:30 – 13:00 | Docs | T30 | Architecture Decision Record (ADR): Pessimistic vs Optimistic Locking | 3.5 | Formal ADR document in /docs folder | BUFFER
24-Sep-2026 | Thursday | 13:00 – 14:00 | Break | - | Lunch & Personal Break | 1 | - | BREAK
24-Sep-2026 | Thursday | 14:00 – 18:00 | Code | T31 | Code refactoring, Sonar/Lint clean-up, dead code removal | 4 | Clean, polished production-ready codebase | BUFFER
25-Sep-2026 | Friday | 09:30 – 11:30 | Demo | T32 | Follow-up review / secondary demonstration with engineering team | 2 | Follow-up demo completed | TO DO
25-Sep-2026 | Friday | 11:30 – 13:00 | Docs | T33 | Finalize deployment runbook & one-command startup script (run.bat / run.sh) | 1.5 | Automated bootstrap scripts | TO DO
25-Sep-2026 | Friday | 13:00 – 14:00 | Break | - | Lunch & Personal Break | 1 | - | BREAK
25-Sep-2026 | Friday | 14:00 – 18:00 | Review | T34 | Pre-delivery sign-off review & code freeze | 4 | Code freeze achieved, zero open defects | BUFFER
28-Sep-2026 | Monday | 09:30 – 13:00 | Docs | T35 | Package Postman Collection, Environment JSON, and sample cURL requests | 3.5 | Exported test assets in repository /docs | TO DO
28-Sep-2026 | Monday | 13:00 – 14:00 | Break | - | Lunch & Personal Break | 1 | - | BREAK
28-Sep-2026 | Monday | 14:00 – 18:00 | Docs | T36 | Executive Summary Presentation (5-slide PowerPoint or Markdown deck) | 4 | Executive slide summary prepared | BUFFER
29-Sep-2026 | Tuesday | 09:30 – 13:00 | Review | T37 | Security & Environment audit: purge test credentials, verify .gitignore | 3.5 | Zero sensitive data in git history | BUFFER
29-Sep-2026 | Tuesday | 13:00 – 14:00 | Break | - | Lunch & Personal Break | 1 | - | BREAK
29-Sep-2026 | Tuesday | 14:00 – 18:00 | Review | T38 | Final dry run on clean checkout & package verification | 4 | Flawless end-to-end verification | BUFFER
30-Sep-2026 | Wednesday | 09:30 – 11:30 | Deliver | T39 | Tag final release: v1.0.0-final-poc & push to master repository | 2 | Git release tagged & pushed | COMPLETE
30-Sep-2026 | Wednesday | 11:30 – 13:00 | Deliver | T40 | Send official completion notification & deliverables link to Rajeev Ranjan | 1.5 | Official delivery email sent | COMPLETE
30-Sep-2026 | Wednesday | 13:00 – 14:00 | Break | - | Lunch & Personal Break | 1 | - | BREAK
30-Sep-2026 | Wednesday | 14:00 – 18:00 | Deliver | T41 | Project POC sign-off archive & transition debrief | 4 | Official POC Sign-Off Complete | DEADLINE
TOTAL PLANNED WORKING HOURS (EXCL. LUNCH)

## Master Task WBS
MASTER WORK BREAKDOWN STRUCTURE (WBS) — 15 CANONICAL POC TASKS
Task ID | Canonical Task Name | Phase | Est. Hours | Planned Day | Priority | Concurrency Relevance | Status
T01 | Read Dapr concepts (Service Invocation, sidecars, app-id) | Learn | 0.5 | Day 1 (Sep 15) | High | Underpins sidecar-to-sidecar HTTP routing | IN PROGRESS
T02 | Install prerequisites (Java 17+, Docker Desktop, Dapr CLI, IDE) | Setup | 0.5 | Day 1 (Sep 15) | High | Ensures Docker engine is ready for 5 containers | IN PROGRESS
T03 | Generate Withdrawal Service code (Spring Boot + Dapr HTTP call) | Code | 1 | Day 1 (Sep 15) | Critical | Exposes /api/withdraw and initiates Dapr hop | IN PROGRESS
T04 | Generate Accounting Service code (JPA + PostgreSQL + Locking) | Code | 1 | Day 1 (Sep 15) | Critical | Implements DB schema and transaction records | IN PROGRESS
T05 | Write Docker Compose + Dapr sidecar configs (5 containers total) | Setup | 1 | Day 2 (Sep 16) | Critical | Withdrawal app, sidecar, Accounting app, sidecar, Postgres | TO DO
T06 | Run docker-compose up --build (resolve first-run config issues) | Setup | 1.5 | Day 2 (Sep 16) | High | Validates inter-container network and Dapr discovery | TO DO
T07 | Verify DB schema + seed data in PostgreSQL | Test | 0.5 | Day 2 (Sep 16) | High | Validates seed account ACC-001 with balance $2,000 | TO DO
T08 | Test happy path via Postman (POST /api/withdraw) | Test | 0.5 | Day 2 (Sep 16) | Critical | Confirms end-to-end deduction of funds | TO DO
T09 | Test error cases (insufficient balance, invalid account) | Test | 0.5 | Day 2 (Sep 16) | High | Validates HTTP 400 when withdrawal > balance | TO DO
T10 | Concurrency test — 10 simultaneous requests, verify DB balance | Test | 1 | Day 3 (Sep 17) | CRITICAL | Proves PESSIMISTIC_WRITE locks prevent race condition | TO DO
T11 | Read & understand generated code (Dapr, locking, @Transactional) | Learn | 1 | Day 3 (Sep 17) | High | Prepares deep technical answers for Rajeev's questions | TO DO
T12 | Add Swagger / OpenAPI UI to both services | Code | 0.5 | Day 1 (Sep 15) | Medium | Provides visual interactive API testing UI | TO DO
T13 | Write README.md (architecture diagram, run instructions, APIs) | Docs | 0.5 | Day 3 (Sep 17) | High | Clear documentation for Rajeev to run on his end | TO DO
T14 | Prepare talking points for Rajeev (Why Dapr? Why locking?) | Demo | 1 | Day 3 (Sep 17) | Critical | Addresses concurrency, sidecars, and architecture tradeoffs | TO DO
T15 | Live demo walkthrough for Rajeev & Nirakar Dash | Demo | 1 | Day 5 (Sep 21) | Critical | Official presentation of the working banking POC | TO DO
TOTAL ESTIMATED CORE HOURS:

## Concurrency & Test Plan
TECHNICAL CONCURRENCY SPECIFICATION & TEST DESIGN
Direct Response to Stakeholder Directive: 'Think from the concurrency perspective if multiple users use these services and DB'
The Race Condition Problem |  | If two users withdraw $500 simultaneously from an account with $600 balance, both threads might read balance = $600 before either writes. Without locking, both deduct $500, resulting in balance = -$400 (Double Spending Disaster).
Solution: Pessimistic Locking |  | Using @Lock(LockModeType.PESSIMISTIC_WRITE) in AccountRepository triggers PostgreSQL SELECT ... FOR UPDATE. The database engine locks the account row until transaction commit/rollback. Concurrent requests queue cleanly in the DB.
Why Not Optimistic Locking? |  | Optimistic locking (@Version) detects conflicts and throws an exception, forcing rollbacks or client retries. In high-contention banking withdrawals, users would experience frustrating failed transactions. Pessimistic locking ensures ordered serialized execution without retries.
Dapr Service Invocation Role |  | Dapr provides mTLS, distributed tracing (W3C trace context), automatic retries with backoff, and transparent service discovery. Withdrawal Service calls http://localhost:3500/v1.0/invoke/accounting-service/method/accounts/{id}/withdraw.
Database Audit Integrity |  | Every withdrawal writes an immutable transaction log record with UUID, balance_before, balance_after, amount, and timestamp within the same @Transactional boundary.
CONCURRENCY LOAD TEST SCENARIO MATRIX
Scenario ID | Test Scenario | Initial Balance | Simultaneous Requests | Expected Outcome | Final Balance | Validation Rule
TC-01 | Single User Happy Path | $2,000.00 | 1 request for $500 | HTTP 200 OK | $1,500.00 | Balance reduced by exactly $500
TC-02 | Single User Overdraw | $100.00 | 1 request for $500 | HTTP 400 Bad Request | $100.00 | Balance untouched, error logged
TC-03 | Concurrent Solvency Test | $1,000.00 | 10 threads x $100 simultaneously | 10 x HTTP 200 OK | $0.00 | Exactly 10 transactions recorded
TC-04 | Race Condition Prevention Test | $1,000.00 | 10 threads x $200 simultaneously | 5 x HTTP 200 OK, 5 x HTTP 400 Bad Request | $0.00 | ZERO negative balance, exactly 5 fail
TC-05 | Concurrent Invalid Account | N/A | 5 threads hitting ACC-999 (Non-existent) | 5 x HTTP 404 Not Found | N/A | Graceful 404 response with zero DB lock leaks