## Timesheet
BANKING MICROSERVICES WITH DAPR — PROJECT TIMESHEET
Java Spring Boot · PostgreSQL · Dapr Service Invocation · Docker Compose
Working Days | Total Hours | Microservices | Total Tasks | New Tech
3 Days | ~12 hrs | 2 Services | 15 Tasks | Dapr Only
Task | Phase | Hours | Status | Day
Read Dapr concepts (Service Invocation, sidecars, app-id) | Learn | 0.5h | To Do | DAY 1
Install prerequisites (Java 17+, Docker Desktop, Dapr CLI, IDE) | Setup | 0.5h | To Do | DAY 1
Generate Withdrawal Service code (Spring Boot + Dapr HTTP call) | Code | 1h | To Do | DAY 1
Generate Accounting Service code (JPA + PostgreSQL + Locking) | Code | 1h | To Do | DAY 1
Write Docker Compose + Dapr sidecar configs (5 containers total) | Setup | 1h | To Do | DAY 1
Run docker-compose up --build (resolve first-run config issues) | Setup | 1.5h | To Do | DAY 2
Verify DB schema + seed data in PostgreSQL | Test | 0.5h | To Do | DAY 2
Test happy path via Postman (POST /api/withdraw) | Test | 0.5h | To Do | DAY 2
Test error cases (insufficient balance, invalid account) | Test | 0.5h | To Do | DAY 2
Concurrency test — 10 simultaneous requests, verify DB balance | Test | 1h | To Do | DAY 2
Read & understand generated code (Dapr, locking, @Transactional) | Learn | 1h | To Do | DAY 2
Add Swagger / OpenAPI UI to both services | Code | 0.5h | To Do | DAY 3
Write README.md (architecture diagram, run instructions, APIs) | Code | 0.5h | To Do | DAY 3
Prepare talking points for Rajeev (Why Dapr? Why locking?) | Demo | 1h | To Do | DAY 3
Live demo walkthrough for Rajeev | Demo | 1h | To Do | DAY 3
⚠ TIGHTEST PART — Day 2: Concurrency test. After 10 simultaneous withdrawals, verify the final DB balance is exactly correct (no double-spend). SELECT FOR UPDATE locking must be active in AccountingService.